## Summary of Work
Schema Creation status
| Orginal table | Completed | Pending | Percentage
No of tables | 51 | 51 | 0 | 100%
Data upload status
| Orginal table | Completed | Pending | Percentage
No of tables | 51 | 42 | 9 | 84%

## Redshist tables-Schema
t.no | Name of mysql table | Name of redshift table | Equivalent Redshift_tables in Stagging ?
1 | _logs | _logs | yes
2 | _tmp_senders | _tmp_senders | yes
3 | a_tmp | a_tmp | yes
4 | alerts | alerts | yes
5 | app_events | app_events | yes
8 | categories | categories | yes
9 | clients_entities | clients_entities | yes
10 | clients_permissions | clients_permissions | yes
11 | clients_senders_groups | clients_senders_groups | yes
12 | clients | clients | yes
13 | custom_reports | custom_reports | yes
18 | devices | devices | yes
19 | domains | domains | yes
20 | domains_tags | domains_tags | yes
21 | ENT_GROUP | ENT_GROUP | yes
22 | ENT_GROUP_DOMAINS | ENT_GROUP_DOMAINS | yes
23 | entities | entities | yes
24 | ENTITIES_DOMAINS | ENTITIES_DOMAINS | yes
25 | ENTITIES_TREE | ENTITIES_TREE | yes
26 | EVENTS | EVENTS | yes
27 | evt_all | evt_all | yes
28 | evt_all_old | evt_all_old | yes
29 | evt_dates | evt_dates | yes
30 | evt_devices | evt_devices | yes
31 | evt_ent | evt_ent | yes
32 | evt_fav | evt_fav | yes
33 | evt_os | evt_os | yes
34 | evt_snd | evt_snd | yes
35 | exceptions | exceptions | yes
36 | favorites | favorites | yes
37 | groups | groups | yes
38 | knex_migrations | knex_migrations | yes
39 | knex_migrations_lock | knex_migrations_lock | yes
40 | long_domains_ids | long_domains_ids | yes
41 | md_senders | md_senders | yes
42 | notifications | notifications | yes
43 | Organizations | Organizations | yes
44 | orgs | orgs | yes
45 | orphan_events | orphan_events | yes
46 | permissions | permissions | yes
47 | roles | roles | yes
48 | roles_permissions | roles_permissions | yes
50 | senders | senders | yes
51 | senders_groups | senders_groups | yes
52 | Settings | Settings | yes
53 | Tags | Tags | yes
54 | tracks | tracks | yes
55 | users | users | yes
56 | users_data | users_data | yes
57 | users_groups | users_groups | yes
58 | users_senders_groups | users_senders_groups | yes

## Status-Uplaoded into redshift
t.no | Name of mysql table | Name of redshift table | data upload in redshift? | Comemnts while Data_upload
2 | _tmp_senders | _tmp_senders | yes
12 | clients | clients | yes
13 | custom_reports | custom_reports | yes
18 | devices | devices | yes
20 | domains_tags | domains_tags | yes
21 | ENT_GROUP | ENT_GROUP | yes
22 | ENT_GROUP_DOMAINS | ENT_GROUP_DOMAINS | yes
23 | entities | entities | yes
25 | ENTITIES_TREE | ENTITIES_TREE | yes
29 | evt_dates | evt_dates | yes
30 | evt_devices | evt_devices | yes
31 | evt_ent | evt_ent | yes
32 | evt_fav | evt_fav | yes
33 | evt_os | evt_os | yes
35 | exceptions | exceptions | yes
36 | favorites | favorites | yes
38 | knex_migrations | knex_migrations | yes
39 | knex_migrations_lock | knex_migrations_lock | yes
41 | md_senders | md_senders | yes
46 | permissions | permissions | yes
47 | roles | roles | yes
50 | senders | senders | yes
53 | Tags | Tags | yes
54 | tracks | tracks | yes
55 | users | users | yes
4 | alerts | alerts | yes
24 | ENTITIES_DOMAINS | ENTITIES_DOMAINS | yes
44 | orgs | orgs | yes
26 | EVENTS | EVENTS | yes
27 | evt_all | evt_all | yes
28 | evt_all_old | evt_all_old | yes
34 | evt_snd | evt_snd | No | extra column found
45 | orphan_events | orphan_events | yes
3 | a_tmp | a_tmp | No | csv is error
5 | app_events | app_events | yes
1 | _logs | _logs | No | data is empty
8 | categories | categories | No | data is empty
9 | clients_entities | clients_entities | No | data is empty
10 | clients_permissions | clients_permissions | No | data is empty
11 | clients_senders_groups | clients_senders_groups | No | data is empty
37 | groups | groups | No | data is empty
42 | notifications | notifications | No | data is empty
43 | Organizations | Organizations | No | data is empty
48 | roles_permissions | roles_permissions | No | data is empty
51 | senders_groups | senders_groups | No | data is empty
52 | Settings | Settings | No | data is empty
56 | users_data | users_data | No | data is empty
57 | users_groups | users_groups | No | data is empty
58 | users_senders_groups | users_senders_groups | No | data is empty
19 | domains | domains | yes
40 | long_domains_ids | long_domains_ids | yes

## Ignore- do not refer
t.no | Name of mysql table | Name of redshift table | CSV_FILES
1 | _logs | _logs | empty
8 | categories | categories | empty
10 | clients_permissions | clients_permissions | empty
11 | clients_senders_groups | clients_senders_groups | empty
37 | groups | groups | empty
42 | notifications | notifications | empty
43 | Organizations | Organizations | empty
48 | roles_permissions | roles_permissions | empty
51 | senders_groups | senders_groups | empty
52 | Settings | Settings | empty
56 | users_data | users_data | empty
57 | users_groups | users_groups | empty
58 | users_senders_groups | users_senders_groups | empty
3 | a_tmp | a_tmp | error
5 | app_events | app_events | error
26 | EVENTS | EVENTS | out of memory
27 | evt_all | evt_all | out of memory
28 | evt_all_old | evt_all_old | out of memory
34 | evt_snd | evt_snd | out of memory
45 | orphan_events | orphan_events | out of memory
9 | clients_entities | clients_entities | yes
12 | clients | clients | yes
2 | _tmp_senders | _tmp_senders | yes
4 | alerts | alerts | yes
13 | custom_reports | custom_reports | yes
18 | devices | devices | yes
19 | domains | domains | yes
20 | domains_tags | domains_tags | yes
21 | ENT_GROUP | ENT_GROUP | yes
22 | ENT_GROUP_DOMAINS | ENT_GROUP_DOMAINS | yes
23 | entities | entities | yes
24 | ENTITIES_DOMAINS | ENTITIES_DOMAINS | yes
25 | ENTITIES_TREE | ENTITIES_TREE | yes
29 | evt_dates | evt_dates | yes
30 | evt_devices | evt_devices | yes
31 | evt_ent | evt_ent | yes
32 | evt_fav | evt_fav | yes
33 | evt_os | evt_os | yes
35 | exceptions | exceptions | yes
36 | favorites | favorites | yes
38 | knex_migrations | knex_migrations | yes
39 | knex_migrations_lock | knex_migrations_lock | yes
40 | long_domains_ids | long_domains_ids | yes
41 | md_senders | md_senders | yes
44 | orgs | orgs | yes
46 | permissions | permissions | yes
47 | roles | roles | yes
50 | senders | senders | yes
53 | Tags | Tags | yes
54 | tracks | tracks | yes
55 | users | users | yes